## RMAP
BAMS RISK MANAGEMENT PLAN
BAMS is working towards an integrated risk management plan that:
· Identifies, analyses, prioritises and effectively manages risk in a way that is consistent with our objectives and resources;
· anticipates threats to services and administration systems;
· identifies plans that ensures the continuity and rapid recovery of services;
· regularly checks the effectiveness of the risk management systems and treatments;
· ensures Board, management and staff actively support and participate in risk management activities.
Our intention is to have:
· compliance with programme requirements and guidelines and legislative requirements;
· effective risk management reporting for ensuring safety and reduced insurance risk exposure.
Risk management audits will cover:
· governance and management;
· financial information and procedures;
· information management;
· workplace health and safety;
· legal and regulatory compliance;
· strategic and operational planning with effective service delivery
· human resource management and cultural competency
BAMS Risk Management Plan 2021 - 2024
RISK RATING: N – NEGLIGIBLE L – LOW M – MEDIUM H – HIGH E – EXTREME |  |  | Likelihood Rating: 1 = Rare 2 = Unlikely 3= Moderate 4 = Likely |  |  | Impact Rating: 1 = Minor 2 = Moderate 3 = Significant 4 = Major
Risk areas | Identified risks & Consequence | Likelihood | Impact | Risk rating | Action to manage risk | Who+ When | Review
Administration/Information Technology (IT)
Filing systems, paper and electronic records management and information management | Need to easily locate documents and information some records are mandated | 3 | 2 | Med | Admin filing systems require general review IT management and housekeeping especially server not well co-ordinated or maintained | Admin, managers, all relevant staff | Agenda item monthly Consider as project time
Correspondence handling or communication | Reviewed and assessed as working well |  |  | N | All mail stamp dated scanned and stored, general mail for staff distributed, filing as appropriate. | Admin | If required
Good management of client records - Client records management is on Communicare | Reviewed and assessed as generally ok but could improve in some areas: Risks: Locum and new GPs not familiar with software |  |  |  | Managers and Administrator to oversee review of files, paper | Admin | Agenda item monthly
Security and back up of records | Unauthorised access to client records or general information not kept confidential |  |  |  | Training sessions for new doctors, nurses, health workers | Q&C Officer
Protection from sabotage |  |  |  |  | Systems to notify and take down access after staff exit – admin checklist | HR
Good maintenance of records/forms procedures etc | Non compliance leads to incorrect or out of date information and agreements | 3 | 2 | Low | Conduct random file audits in May & September | Admin | Agenda item monthly
Security or back up on electronic records | Nil issue |  |  | N | EXTERNAL IT contractors, daily back up and cloud storage | Finance/IT contractor | Agenda item monthly
Include breach of privacy and data legislation in orientation policy and process, inservice updates
Timed control of screens and not leaving screens open and unattended
Maintenance of computer systems | Computers well maintained
Adequate insurance cover and/or monitoring | All insurances are up to date |  |  |  | Schedule of Insurances is documented, renewal dates logged documents provided for Board. |  | Annually
Planning for replacement (IT contractors)
authorised licences
Finance controlled by WAMS with Risk Management in place
Need to have an ability to generate or attract funds | Require funds to keep operating at current level | 3 | 2 | Med | Current level for 3 years.
Poor management of Medicare coding & invoicing
Lack of capacity for delivery of funded programs
Effective and regular financial planning and monitoring | Avoidance of Budget overruns | 2 | 2 | Low | Monthly budget review against expenditure each meeting monthly, working towards and bringing payroll Monthly analysis identifies any over rums and reports on these. Trustees can access accounts daily | Coordinator and Finance | Monthly
| Budget review against expenditure monthly, work towards 2 weekly payroll |  |  |  | Visits by Westpac information on budgetting for staff
Multiple quotes for capital works and trade assistance
Effective financial record keeping and reporting | To enable good decisions by COM | 2 | 2 | Low | Monthly reporting including monthly P&L, Balance Sheets, consolidated and split accounts, term deposit analysis, consolidates account analysis for month and year to date.
Work towards % budget expended and variance reporting
Effective controls and procedures | To avoid unauthorised expenditure or fraud | 2 | 2 | Low | 3 of five signatures for expenditure, process of payroll Transfer of funds – daily transaction limit, as above with 2 signatures for movement between accounts within budget limits. Annual external audit. Reimbursement upon receipt presentation etc. Limitations to financial authority detailed. Schedule of delegations to enable limitations to authority. |  | Monthly
Develop Fraud and Corruption policy
Unanticipated expenses or inadequate provisions being made for potential expenses (e.g. award increases, paid maternity leave) | Preparation to avoid any inability to pay bills/insolvency | 2 | 2 | High | Term deposit unable to be maintained. Budget includes likely expenses. No surplus funds to cover any unanticipated expenses. Reserve funds, all accruals in hand |  | Monthly
Governance - WAMS Board
Need adequate compliance and administration of incorporation requirements (e.g. constitution, member records etc) common seal | Failure to lodge compliance documents could lead to member disputes, legal challenges/de-registration | 2 | 2 | Low | Compliance check, AGM, policy and procedure, copy of Charities Commission requirements, annual review of Legal responsibilitises under Act. | CEO | Annually
[5 empty] | Form 15 post AGMs renumerations – set level and schedule of payments for activites and travel – signed attendance records minuted | Finance
| Strategic planning |  |  |  | now require external overview | Board
If Board unable to form a quorum on a regular basis | Organisation no longer viable | 3 | 3 | Med | Adequate numbers with back up of Strategic Director if absolutely necessary. Apologies placed prior to meeting allows for date change. Documentation required for each meeting and AGM re number of attendances of each member, policy re attendances and failed attendances. Planning to seek new members. |  | As and if required
Aim to avoid or plan for a potential lack of skills on committee | May lead to confusion and/or lack of proper procedures | 2 | 2 | Low | Seek an Advisory Group for additional skill set or for checking information/concerns independently. Trustees are invited to be on the Board and have appropriate skill set. |  | Annually
Lack of adequate information being provided to committee | Poor decisions may be made by committee | 2 | 2 | Low | Board has unrestricted access to financial accounts and receives information as detailed in reports each month and quarter, must meet at minimum times per year | Director | 2011-11-30
Finance
Inadequate procedures for dealing with conflicts of interest | Disputes arising or unfair decisions being made | 2 | 1 | Low | Conflict of Interest Policy, declaration of conflicts at Trust meeting, each reviewer must declare prior to reviews, employee registered, Code of Conduct and Ethics Agreement signed by each trustee and employee as part of orientation and employment. | All | As described
Loss or damage resulting from inadequate monitoring by committee | Lack of implementation follow-up for action items arising from meetings | 2 | 2 | Low | Meeting agenda to capture decisions and any required follow up (action/discussion/information) from previous meeting. | Director | Monthly
Quarterly
Human resource
Adequate personnel policies or procedures | Staff disputes and problems | 2 | 1 | Low | Detailed personnel policies and procedures – recruitment, supervision, staff development, disciplinary, disputes resolution | HR | 6 monthly review (as needed)
Adequate skills, knowledge or understanding of job requirements by staff | Poor service delivery, staff performance or client complaint | 2 | 1 | Low | Each position has PD each employee signs and receives copy of PD. Orientation and mentoring Effective evaluation/feedback and complaints management system | HR CEO Program Managers | As recruited and annual appraisal
AMSED | St not aware of mandatory requirements etc | 2 | 2 | Med | Ensure modules on knowledge for mandatory traning eg WWC | Managers | monthly
WHS
Procedure to avoid inappropriate behaviour by staff or volunteers | Client, staff or volunteer complaint or concern | 1 | 2 | Low | Effective Policies and procedures for Harrassment, bullying, inappropriate behaviour by staff/volunteer. Probity checks completed. White Ribbon Accreditation etc | Board CEO Managers all staff | Ongoing and per event
Avoid poor workplace conditions or breaches of Workplace Health and Safety | Injury or illness of staff or volunteers; Legal action against the organisation | 2 | 2 | Med | Effective OHS guidelines, risk assessments for individual consumers, effective monitoring systems for risk and reduction of risk situations. Presented to COM monthly, tabulated in AGM report. | CEO Board Managers | Ongoing and per event
Environmental circumstances | Water security – demands for water allowance | 1 | 1 | High | Work with local authorities to address water shortages and impact of cotton farming | Board CEO others as appropriate | As the rains keep falling and the river is and has been high, water is no longer an issue until the next drought. Rainwater tanks have been invested in to catch rain water from the ND
Revisit budget and plan for payment of water allowance to clinical staff
Avoid Poor recruitment procedures or staff succession planning | Positions remaining vacant for extended periods | 3 | 2 | Low | Follow all policies and procedures planning for coverage of primary positions such as case co-ordinator, payroll admin etc. | HR CEO Board | Monthly
Staff complaints or disputes handling | Disruption to operations; Escalation to legal action | 3 | 2 | Low | Effective staff complaints handling system, | Board CEO Managers all staff | Ongoing and per event
Avoid inadequate knowledge succession/ transfer processes | Loss of critical knowledge when key personnel leave | 3 | 2 | Low | Succession policy in effect, team is interdisciplinary - staff share roles and can cross over as required. Handovers as much as possible | CEO HR
Board
Maintain effective lines of communication throughout the organisation | Loss or organisational performance, disputes or staff confusion | 3 | 2 | Low | Regular staff meetings agenda control and preparation – team cohesion and early raising or issues | All | Ongoing
Ensure good record keeping (eg documented job contracts, nil errors in staff entitlements) | Staff complaint or industrial action | 3 | 2 | Low | Effective HR management, errors in payroll corrected asap within 24hrs. | Coordinator & Finance
Legal
Lack of compliance with legislation related to safety and protection | Injury or harm to individuals; Legal action against organisation | 3 | 2 | Low | Policies updated | Directors | Annually
[5 empty] | Legislation revised and legislation Schedule updated Yearly | HR | Checks as per recruitment
Police, Working with Children and/or Vulnerable Persons Checks,
Lack of compliance with anti discrimination legislation in employment or services | Unfair outcomes for individuals; Legal action against organisation | 2 | 2 | Low | Anti Discrimination policy and processes (exemption for Aboriginality) | HR | Ongoing and per event
Lack of compliance in information management and record keeping | Legal action against organisation for breach of privacy | 2 | 2 | Low | Effective processes in place for the maintenance of privacy and release of /sharing of information on an individual basis.
Lack of compliance with industrial requirements (including wages and entitlements) | Staff complaint or industrial action | 2 | 2 | Low | Effective processes in place with yearly external auditing
Lack of taxation compliance (including deductions, superannuation, GST etc) | Legal action or fines | 1 | 2 | Low | Effective processes in place and external audit yearly
Inadequate monitoring of other legal requirements and obligations | Breaches of law or obligations; Legal action or fines | 2 | 1 | Low | Yearly monitoring of legislative schedule
Inadequate procedures for establishing contracts | Contractual obligations incurred by the organisation without proper authority | 3 | 2 | Low | Policies , procedures, reporting and external review re contractual obligations
Inadequate procedures for monitoring contract compliance | Breaches of contract (including funding agreements); Legal action and/or financial loss | 2 | 2 | Low | Contract compliance monitored through monthly report to COM and as above
Accreditations |  |  |  |  | White Ribbon / Clinic /organisation
Professional development
Management and operations, Service Delivery
Lack of adequate policies, appropriate documentation or policy implementation | Loss, damage or poor organisational performance | 1 | 2 | Low | Policy reviewed 3-yearly or as otherwise stated. New policies disseminated to staff for comment, training in new policies. | CEO HR Managers | As required for review and new
Inappropriate or inadequate client service provision | Client complaint or legal action | 2 | 2 | Low | Clear guidelines for service delivery operations and reduction of risk factors. 3 identifiers before bloods etc checks on expired pharmacy and equipment and general items | Managers and clinic staff | Ongoing
Clinical Recall | Lack of safe systems and capacity to maintain recall appointments – breach of legislation and potential death of client |  |  | High | Ensure adequate capacity to maintain system
Infection Control | Lack of procedures and following guidelines |  |  |  | Up-to-date information and guidelines
Monitor implementation
Lack of Clinical Governance | Safe clinical practice |  |  |  | Establish clinical peer review systems that accommodate locums and high staff turnover – currently have senior medical officer
Recruiting and retaining registered nurses
Structure of clinical appointments | Impacts on ability to cliam income |  | 3 | Med-High | Assist in maximising Medicare claims and mitigates risk in loss of funding
Lack of compliance with service provision standards | Loss of accreditation and/or funding; Damage to organisational reputation | 1 | 2 | Low | Maintenance of accreditation Standards and protocols, staff trained in standards. Report each month via the incident reports. Staff disciplinary procedure. Clarifiy reporting of concerns and progressing invesigations.
Inadequate feedback mechanisms or service quality monitoring | Consumer dissatisfaction or poor service quality occurring without senior staff or Board being aware | 1 | 2 | Low | Regular client satisfaction survey at training and reviews, reports to accreditors etc
Poor planning and inadequate monitoring of organisational plans |  |  |  |  | Organisational plans managed each month report and review progress
Covid Response Plan | For the smooth response in the case of an outbreak within staff. | 4 | 3 | Med-High | Hand Sanitiser at numerous points and on all desks and masks provided. Prioritise staff immunisation Weekly RAT testing for all staff, if positive a PCR to confirm then isolation. Aim to have staff adaptable to fill in where and if necessary. This response is also included in Emergency Plan. Staff to be made aware or Government assistance whilst isolating. | All staff with Managers assistance until risk is minimised. | Ongoing as Covid continues.
GPRC - Respiratory Clinic | Protection of staff performing the testing from getting Covid | 4 | 3 | Med-High | Immunisation and full PPE worn during testing including face shield, gowns and gloves with hand sanitiser readily available at numerous points. | All staff with Managers assistance until risk is minimised. | Ongoing as Covid continues.
Emergency Response Plan | For the smooth response in the case of an emergency the plan needs to be kept up to date. | 3 | 3 | Med | Regular review of the plan and staff updated.
Physical
Inadequate safety precautions being taken or hazard assessment being made of environment and equipment (including grounds & buildings, vehicles & equipment, procedures & practices) | Injury to individuals; Legal action against organisation | 3 | 2 | Low | Risk assessment practices and OH&S site inspections etc for individual and group circumstances.
Visitor accommodation and communication re visitor comings and goings |  |  |  |  | Accommodation list on server of permanent residents – comings and goings
Duress alarms for clinic and consulting rooms | Potential assault and staff/client injury | 2 | 2 | Low | Investigate installation of duress alarms and USB system |  | Little and Big Green buttons installed and working via the desktop in each room. The consult rooms have a Big Green button in case the desktop goes to sleep.
Ensure all staff are aware of the alarm sound and process to follow
Inadequate procedures for handling dangerous or hazardous chemicals | Injury to individuals; Legal action against organisation | 1 | 2 | Low | No chemicals handled – locked doors on cleaning cupboard
photocopier toner in sealed capsule – external cleaners.
Poor ergonomics of work furniture and equipment | Injury to individuals; Legal action against organisation | 3 | 2 | Low | Part of regular workplace hazard assessment Equipment required for improved ergonomics can be purchased.
Inadequate procedures for infection control | Staff or visitors falling ill; closing due to outbreaks of infectious disease | 1 | 2 | Low | Effective infection control procedures and communicable diseases procedures.
Inadequate security for premises | Loss due to theft | 3 | 2 | Low | Personal and facility security system, key lock boxes, internal key lock box. Personnel sign for keys and return upon termination.
Inadequate procedures for handling accidents or critical incidents | Accidents or injuries without notification being made to the appropriate people | 1 | 2 | Low | All staff trained to notify any incident through reporting systems – initially verbally then documented in appropriate form. | Manager to assist and CEO and COM notified for follow up if required.
Safe staff visitation with clients in New Development | Staff isolated with client; increase risk of harm | 2 | 2 | Low | Personal safety plans, awareness of locations and times of appointments, 2 staff to be present in the building, risk assessment prior to visit. | Manager to be aware of appointment and allocate a reception staff to be present in the required buidling
Safe driving and home visits | Staff isolated with client; increase risk of harm | 2 | 2 | Low | Personal safety plans, awareness of locations and times of home visits, 2 staff for home visits, risk assessment of home prior to visit.